## Methodology
BrightPath Recruitment Ltd — Information Security Risk Assessment
Fictional demonstration project for portfolio purposes. BrightPath Recruitment Ltd is not a real organisation.
Scope & context | BrightPath Recruitment Ltd: a 25-person recruitment agency in Reading, UK (office + hybrid working). Holds CVs, passport scans and salary details of ~8,000 candidates in a cloud CRM. Uses Microsoft 365; staff access work email on personal phones (BYOD); an AI tool screens CVs automatically. No dedicated security team. Assessment covers information security and data protection risks to candidate data, business operations and regulatory compliance.
Approach | This assessment follows the ISO 31000:2018 risk management process: establish context → risk identification → risk analysis → risk evaluation → risk treatment. Risks were identified through review of the business context (assets, threats, vulnerabilities) and analysed using a 5×5 likelihood × impact matrix. Risk Score = Likelihood × Impact.
Likelihood scale | 1 Rare (unlikely within 5 years) ¦ 2 Unlikely (may occur within 2–5 years) ¦ 3 Possible (may occur within 1–2 years) ¦ 4 Likely (expected within 12 months) ¦ 5 Almost certain (expected within 6 months or already occurring)
Impact scale | 1 Negligible (minor inconvenience, no data exposed) ¦ 2 Minor (limited internal disruption) ¦ 3 Moderate (small-scale candidate data exposure, ICO notification considered, <1 day disruption) ¦ 4 Major (significant candidate data exposure, ICO reportable, reputational damage, multi-day disruption) ¦ 5 Severe (large-scale breach of ~8,000 candidate records incl. passport scans, ICO enforcement/fine, loss of key clients, existential business interruption)
Risk evaluation bands | Score 15–25 = HIGH: treat immediately, escalate to Managing Director. Score 8–12 = MEDIUM: treat within 6 months. Score 1–6 = LOW: accept and monitor at next annual review.
Treatment options | Avoid (stop the activity) ¦ Reduce (apply controls to lower likelihood and/or impact) ¦ Transfer (shift via contract or insurance) ¦ Accept (document and monitor, within appetite)
Review | Register owner: Managing Director. Review cycle: annual, or after any significant incident or change (new system, new vendor, office move).
5×5 risk matrix
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5

## Risk Register
Risk ID | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Score | Existing Controls | Treatment | Recommended Control | Owner
R-01 | Recruiter M365 mailboxes and credentials | Phishing email harvesting login credentials | MFA not enforced on M365 or CRM; no security awareness training | 4 | 4 | 16 | Default M365 spam filtering only | Reduce | Enforce MFA on all M365 and CRM accounts; quarterly phishing-awareness training with simulated phishing tests | Office Manager
R-02 | Candidate database in cloud CRM (~8,000 records incl. passport scans) | External attacker or accidental public exposure of candidate data | CRM sharing/permissions never reviewed; all staff have full export rights; no audit logging enabled | 3 | 5 | 15 | CRM vendor default security settings | Reduce | Permissions review against least-privilege; restrict bulk-export to two named roles; enable and monitor CRM audit logs | Managing Director
R-03 | Candidate data in work email on personal phones (BYOD) | Loss or theft of an unmanaged personal device | No mobile device management; encryption and screen-lock not enforced; no remote-wipe capability | 4 | 4 | 16 | None — informal staff guidance only | Reduce | Deploy Microsoft Intune (included in M365 Business Premium): enforce PIN, device encryption and selective remote wipe of work data | Office Manager
R-04 | M365 and CRM user accounts | Unauthorised access by former staff | No formal leaver process; accounts found active after departure; one shared CRM login in use | 4 | 4 | 16 | Ad-hoc deactivation when remembered | Reduce | Joiner/mover/leaver checklist with same-day deactivation; eliminate shared login; quarterly user-access review | Office Manager
R-05 | All company data and day-to-day operations | Ransomware delivered via malicious CV attachment | Recruiters routinely open unsolicited attachments; no endpoint detection; backups never test-restored | 3 | 5 | 15 | Default Microsoft Defender antivirus; OneDrive sync | Reduce | Microsoft Defender for Business with Safe Attachments sandboxing; documented backup regime with quarterly test restores | External IT provider
R-06 | AI CV-screening tool and candidate selection decisions | Discriminatory screening outcomes against protected groups (Equality Act 2010; UK GDPR Art. 22) | Tool deployed without bias testing, DPIA or human review of automated rejections | 3 | 4 | 12 | Vendor marketing claims only | Reduce | Mandate human review of all AI rejections; complete DPIA before further use; obtain vendor bias-testing and model documentation | Managing Director
R-07 | Passport scans and ID documents of rejected candidates | ICO enforcement for breach of UK GDPR storage limitation principle | No retention schedule; rejected-candidate data incl. passport scans kept indefinitely | 4 | 3 | 12 | None | Reduce | Retention schedule (e.g. delete 6 months after final decision unless consent to retain); automated CRM deletion workflow | Managing Director
R-08 | Company laptops used for hybrid working | Loss or theft of laptop in transit or public places | Disk encryption status unknown; no asset register; no screen-lock policy | 3 | 4 | 12 | Windows login passwords | Reduce | Enforce BitLocker via Intune; maintain asset register; auto screen-lock at 5 minutes | Office Manager
R-09 | Candidate CVs and personal data in transit | Data leakage via unapproved channels (personal email, WhatsApp) | No acceptable use policy; no data loss prevention controls; habit of forwarding CVs to personal accounts | 4 | 3 | 12 | None — verbal expectations only | Reduce | Acceptable Use Policy (Artefact 2); M365 DLP policy detecting passport numbers and bulk candidate data in outbound mail | Office Manager
R-10 | CRM vendor and AI screening vendor (third parties) | Breach or failure at a vendor holding BrightPath candidate data | No due diligence performed; data processing agreements not reviewed; vendor security posture unknown | 2 | 5 | 10 | Standard vendor contracts | Transfer | Vendor security questionnaire; verify ISO 27001/SOC 2 certification; review and sign GDPR-compliant data processing agreements with liability clauses | Managing Director
R-11 | Business operations (placements, payroll deadlines) | Extended outage of M365 or cloud CRM | Sole reliance on cloud vendors; no documented continuity arrangements | 2 | 4 | 8 | Vendor SLAs (99.9% availability) | Accept | Accepted within appetite given vendor SLAs; document key contacts and a manual workaround one-pager; reassess at annual review | Managing Director